## Slide 1
IRAD Update 15 Mar 23

## Slide 2: Recursive Receiver
  This project is aimed to investigate the potential and applications of IIR filters in EW components.
Infrastructure
Item
USRP B210 (Radio)
Laptop
Antennas: Log Periodic / Monopole
Coaxial cables
GNU-radio software

## Slide 3: Recursive Receiver
Personnel
Level | Name | LoE | Allocated hours | Spend hours | Spend time
Expert | Hugh Kennedy | 0.2 | 121.6 | 13 | 10.69%
Mid-level | Diego Lozano | 0.4 | 243.2 | 67.6 | 27.80%
Junior | Swapnil Srivastava | 0.6 | 364.8 | 111.5 | 30.56%
Current: stage 2 – Phase 1
  RF design and testing: basic digital filters, modulation/demodulation using the USRP & GNU-radio.
  RF measurements, SNR, noise floor.
  Reading and simulation of polyphase filter-bank (Multirate)
  Implementation of a FMCW radar
  The allocated hours is based on the timeframe from 30 JAN 23 to 19 MAY 23 (15 weeks 4 days)

## Slide 4: Differential LPI DSP
  This project is aimed to investigate and create novel radio-techniques using machine learning. This can be accomplished by characterization transmission impairments and modeling of RF systems with auto-differentiable blocks that allow gradients to backpropagate from an objective function.
Infrastructure
Item
Desktop computer
Server
GitHub repository
Visual Studio Software
Python 3.10 programming language

## Slide 5: Differential LPI DSP
Personnel
Level | Name | LoE | Allocated hours | Spend hours | Spend time
Expert | Daniel Gibbons | 0.2 | 182.4 | 17.8 | 9.76%
Mid-level | Diego Lozano | 0.4 | 273.6 | 60.0 | 21.93%
Junior | Tim Kral | 0.6 | 258 | 0 | 100.00%
Current: Establish DSSS baseline
  Implement the Received and transmitter DSSS @ baseline
  Simulate a simple transmission with AWGN
  Optimize the receiver gain based on gradients to recover the transmitted message.
  Add channel distortion effect
  The allocated hours is based on the timeframe from 06 FEB 23 to 30 JUN 23 (20 weeks 4 days)

## Slide 6: FPECM Power measurement
  This project is aimed to provide automated characterization of transmitted RF energy in both angle of arrival and distance. It will then transfer the measured RF energy to usable polar plots.
Infrastructure
Item
Desktop computer
Robot
SDR: HackRF One
Antennas & LNA
Raspberry Pi
GNU-radio software

## Slide 7: FPECM Power measurement
Personnel
Current: Establish DSSS baseline
  Implement the Received and transmitter DSSS @ baseline
  Simulate a simple transmission with AWGN
  The allocated hours is based on the timeframe from 22 AUG 22 to 31 MARCH 23 (31 weeks 4 days)
Level | Name | LoE | Allocated hours | Spend hours | Spend time
Expert | Aaron Debono | Closed | 0.5 | Closed | Closed
Expert | Aaron Logue | 0.1 | 65.5 | 66 | 100.76%
Junior | Nicholas Paczynski | 0.6 | 693 | 636.1 | 91.79%
Junior | Sean Priestley | 0.6 | 72 | 31 | 43.06%

## Slide 8: FPECM Power measurement
Overview
  The FPECM RF power measurement task has continued to move ahead with Nick making good progress over the last couple of weeks. This has been primarily on the distance robot which houses the receiver.
Personnel
  Nicholas Paczynski – Will remain on task until 1 Feb 23 at close to 1 FTE (some hours assigned to upskilling for MMEW in Feb). At this stage Nick will be tasked at 0.5 FTE on MMEW. Nick could continue with the IRAD task to fill the 0.5 FTE remaining until other tasking is found for him. This has not been budgeted for.
  Aaron Logue - I provided support up to and just after the Xmas break to enable Nick to progress at a faster rate and to provide guidance on development techniques. This included the use of additional hours (18) as requested at the pre-Xmas IRAD meeting.
Infrastructure
  Most of the hardware has arrived with some small items outstanding. At this stage this can be worked around.

## Slide 9: Recommendations
  Improve the project traceability
  Include systematic progression sub-tasks/Stages on mis or defined by project managers
  Conduct a monthly/fortnightly review about the learned or required skills. Each team member can fill a questionary or writing 1 or 2 paragraphs about the learned or required skills.
      Identify key skills needed for a particular task.
      They can have benefits in the short term.
      Offer diverse perspective about stage of the project
  Improve the project documentation
  Create a template document with defined sections such as the abstract, background information, process & methods and findings.
  It can be a dynamic document that can be continually edited and updated by all-project members.

## Slide 10: Recommendations
  Improve the workshop installation
  Get shelf or organizer for tools and equipment
  Include systematic progression sub-tasks/Stages
  Conduct a monthly/fortnightly review about the learned or required skills. Each team member can fill a questionary or writing 1 or 2 paragraphs about the learned or required skills.
      Identify key skills as they can have benefits in the short term.
      Offer diverse perspective about stage of the project
  Improve the project documentation
  Create a template document with defined sections such as the abstract, background information, process & methods and findings.
  It can be a dynamic document that can be continually edited and updated by all-project members.

## Slide 11: Conduct research and development
Systematic progression of work
  Conduct a literature review
  Find the gap (Knowledge/ technology)
  Formulate a Hypothesis
  Design experiments
  Analyse experiment results
  Logical conclusions

## Slide 12: Conduct research and development
Trial and Error method
Advantages | Disadvantages
Effective for short term tasks | Time consuming
A good learning method | Waste of resources
Simplest applications | Unpredictable
 | Brute force

## Slide 13: Conduct research and development
Systematic progression of work
  Conduct a literature review
  Find the gap (Knowledge/ technology)
  Formulate a Hypothesis
  Design experiments
  Analyse experiment results
  Logical conclusions

## Slide 14: Advantages
R&D Tax Incentive supported
  Supported by the Australian government
  Tax offset rates depends on the company aggregated turnover (Thr= $ 20 Million)
  Meet the criteria