## Slide 1
IRAD Update 23 Mar 23

## Slide 2
Recursive Receiver project
UNOFFICIAL
  This project is aimed to investigate the potential and applications of recursive filters in EW components.
 | INFRASTRUCTURE
 | USRP B210 (Radio)
 | Laptop
 | Antennas: Log Periodic / Monopole
 | Coaxial cables
 | GNU-radio software
  Figure 1. FM broadcast band Spectrum detection using GNU-radio

## Slide 3
Recursive Receiver project
UNOFFICIAL
LEVEL | NAME | LoE | ALLOCATED HOURS | SPEND HOURS | SPEND TIME
Expert | Hugh Kennedy | 0.2 | 121.6 | 13 | 10.69%
Mid-level | Diego Lozano | 0.4 | 243.2 | 67.6 | 27.80%
Junior | Swapnil Srivastava | 0.5 | 364.8 | 111.5 | 30.56%
Chart: 
| Direction finding | Signal detection | Demodulation | Spectrum sensing
. | 45007 | 44972 | 44972 | 44959
Duration | 58 | 70 | 51 | 76
  Task Name
Project Timeframe (30-Jan-23 to 19-May-23)
  Swapnil - Start
  Diego - Start
47.70%

## Slide 4
PRESENTATION POINTS
UNOFFICIAL

## Slide 5: Recursive Receiver
Personnel
Level | Name | LoE | Allocated hours | Spend hours | Spend time
Expert | Hugh Kennedy | 0.2 | 121.6 | 13 | 10.69%
Mid-level | Diego Lozano | 0.4 | 243.2 | 67.6 | 27.80%
Junior | Swapnil Srivastava | 0.6 | 364.8 | 111.5 | 30.56%
Current: stage 1 – Phase 1
  RF design and testing: basic digital filters, modulation/demodulation using the USRP & GNU-radio.
  RF measurements, SNR, noise floor.
  Reading and simulation of polyphase filter-bank (Multirate)
  Implementation of a FMCW radar
  The allocated hours is based on the timeframe from 30 JAN 23 to 19 MAY 23 (15 weeks 4 days)

## Slide 6: Differential LPI DSP
  This project is aimed to investigate and create novel radio-techniques using machine learning. This can be accomplished by characterization transmission impairments and modeling of RF systems with auto-differentiable blocks that allow gradients to backpropagate from an objective function.
Infrastructure
Item
Desktop computer
Server
GitHub repository
Visual Studio Software
Python 3.10 programming language

## Slide 7: Differential LPI DSP
Personnel
Level | Name | LoE | Allocated hours | Spend hours | Spend time
Expert | Daniel Gibbons | 0.2 | 182.4 | 17.8 | 9.76%
Mid-level | Diego Lozano | 0.4 | 273.6 | 60.0 | 21.93%
Current: Establish DSSS baseline
  Implement the Received and transmitter DSSS @ baseline
  Simulate a simple transmission with AWGN
  Optimize the receiver gain based on gradients to recover the transmitted message in a simple transmission.
  Add channel distortion effect and implement a new architecture.
  The allocated hours is based on the timeframe from 06 FEB 23 to 30 JUN 23 (20 weeks 4 days)

## Slide 8: FPECM Power measurement
  This project is aimed to provide automated characterization of transmitted RF energy in both angle of arrival and distance. It will then transfer the measured RF energy to usable polar plots.
Infrastructure
Item
Desktop computer & Laptop
Driving Robot & Rotating Platform
SDR: HackRF One
Antennas, LNA & RF switch
Raspberry Pi, UPS, Li-Ion Battery
GNU-radio software

## Slide 9: FPECM Power measurement
Personnel
Current:
Developing a final major component – Line following script using IR sensors, this script has to be compatible with the motor script. - RF components, motor drive, and the state machine are operating. He needs to refine the Python scripts, - Generate report
Getting familiar with the project and learning Python programming language. Possible challenges in developing some mechanical components.
  The allocated hours is based on the timeframe from 22 AUG 22 to 31 MARCH 23 ()
Level | Name | LoE | Allocated hours | Spend hours | Spend time
Expert | Aaron Debono | Closed | 0.5 | Closed | Closed
Expert | Aaron Logue | 0.1 | 65.5 | 66 | 100.76%
Junior | Nicholas Paczynski | 0.6 | 693 | 636.1 | 91.79%
Junior | Sean Priestley | 0.2 | 72 | 31 | 43.06%

## Slide 10: Recommendations
  Project traceability
  Include systematic progression sub-tasks/Stages on mis or defined by project managers
  Conduct a monthly/fortnightly review (Reflection) about the learned or required skills. Some team members can fill a questionary or writing 1 or 2 paragraphs about the learned or required skills.
      Identify key skills needed for a particular task.
      They can have benefits in the short term.
      Offer diverse perspective about stage of the project
  Project documentation
  Create a template document with defined sections such as the abstract, background information, process & methods and findings.
  It can be a dynamic document that can be continually edited and updated by all-project members.

## Slide 11: Recommendations
  Encourage Junior members to follow the Engineering method
 | Stage | Description
1 | Idea | Identify the problem
2 | Concept | Conduct a literature review to find existing solutions, requirements, Limitations, find the knowledge/ technology gap
3 | Planning | Define objectives, plan a program and schedule tasks (Gantt and Pert charts)
4 | Design | Translate requirements and the model into engineering specifications to design and build a working prototype models
5 | Development | Generate the engineering documentation such as schematics, source code into a prototype that demonstrates the solution to the problem.
6 | Launch | Release of the engineering design and documentation package to manufacturing facilities for production

## Slide 12: Recommendations
Government Grants and Incentive
R&D Tax Incentive supported
  Supported by the Australian government
  Tax offset rates depends on the company aggregated turnover (Thr= $ 20 Million)